## Purpose-Instructions
Getting Started in 340B Checklist
Purpose:
The purpose of this tool is to outline compliance and operational considerations for new 340B covered entities. Although all covered entities are likely to have differences in how they set up their programs, the areas covered in this tool will help sites understand the primary areas to consider.
This tool will:
• Focus on compliance, education and training, and purchasing optimization elements critical for sites to consider during implementation of the 340B Program • Reference helpful materials and resources available from the PVP in understanding and operationalizing the 340B Program • Serve as a project management tool during implementation (optional) Note: This tool focuses on the steps for a covered entity to get started in the 340B Program; it does not address the steps needed to implement contract pharmacy. Additional steps may be required for contract pharmacy implementation.
Instructions:
• This tool is a template that your sites can add to/remove from based on which areas align to the way your program will be developed; customize it to best fit your needs based on the operations at your individual site. • Use the filters in columns E-I to organize the chart for desired time period of implementation (e.g., Prior to Going Live or Within First 3 Months).These are general timeframes; sites should customize timelines for tasks based on individual needs. • Use the headers in column A to help determine which person on your team may be responsible for those tasks based on the area of focus; another option could be to separate each of these task areas into different tabs of this document to allow easier visualization if different staff members will be responsible for each area. • Once the proper timeframe and tasks are identified, review each task and follow the instruction in the "How To" section; follow the links in column D to find more detailed instructions/education for each of these areas. • Certain tasks will reference 340B tools on the PVP website. Click the link to access the tools page, then expand the covered entity type and select the specified tool. • Tasks will also have links to HRSA, 340B PVP website pages, and videos to assist with the process. • Some tasks also have additional information available in cell comments that further elaborate on considerations related to that area. • (Optional) Use the final three columns as a Project Management Tool.
Project Management Tool (Optional):
• Use the final three columns as a record for the project implementation progress. • Review each task and assign it to a team member in the "Assign To" column. • Determine a timeline and document the due date in the "Complete By" column. • Document progress in the "Project Status" column.
This tool is written to align with Health Resources and Services Administration (HRSA) policy, and is provided only as an example for the purpose of encouraging 340B Program integrity. This information has not been endorsed by HRSA and is not dispositive in determining compliance with or participatory status in the 340B Drug Pricing Program. 340B stakeholders are ultimately responsible for 340B Program compliance and compliance with all other applicable laws and regulations. Apexus encourages all stakeholders to include legal counsel as part of their program integrity efforts.
© 2024 Apexus. Permission is granted to use, copy, and distribute this work solely for 340B covered entities and Medicaid agencies. 02292024

## Covered Entity Checklist
Getting Started in 340B Checklist
Project Management Tool
Category | Task | How To/Resource | Links | Prior to Registration | Prior to Going Live | Within First 3 Month | Within First Year | Ongoing | Assigned To | Complete By | Project Status
Compliance Related
CR - 1 | Determine site eligibility in anticipation of registration | Once your covered entity (CE) has been determined to meet the eligibility for the 340B Program (https://www.hrsa.gov/opa/eligibility-and-registration/index.html), meet with the individual(s) responsible for maintenance of your grant information to document eligibility criteria and gather supporting documentation for registration.Work with your reimbursement/billing office to understand what NPIs are used for billing in each location/setting that will be using 340B purchased medications. |  | X
CR - 2 | Assemble expertise needed to make implementation decisions | The 340B Program affects many different areas of the organization. Expertise from multiple areas may be needed to make critical decisions about 340B Program implementation. This list is not all inclusive but includes areas that best practice sites involve early to make informed decisions. Pharmacy: typically responsible for the oversight of the medications Reimbursement: critical to gathering a list of NPIs for registration Billing: important for assessing billing needs for Medicaid and Medicare if 340B product used Legal: will help in development of policies and procedures (P&Ps) and key programmatic decisions Compliance: assist in developing self-audit procedures and processes for responding to noncompliance |  | X
CR - 3 | Determine which inventory model(s) will be used at your site(s) | Broadly, there are three inventory models: replenishment (or neutral) inventory, physical inventory, or hybrid. Most grantees utilize physical intentory models in their clinics and/or retail pharmacies. If utlizing a contact pharmacy, that contract pharmacy may require a replenishment model and the use of a third party administrator (TPA) to manage that inventory. Models may be different based on setting and operational need. |  | X
CR - 4 | Develop entity-specific policies and procedures | Prior to going live, entities should have policies and procedures that outline how they will align to core elements of the program. Entities may need to assess certain areas mentioned in this tool early in the process when determining operational infrastructure. |  | X
CR - 5 | Determine whether your sites will carve in or carve out Medicaid | At registration, CEs will need to articulate which states and which NPIs are using 340B purchased medications when billing Medicaid fee for service (FFS) (known as "carving in" Medicaid). The decision to carve in or out depends on an individual site's circumstances; all sites should work with their billing and reimbursement offices to understand which state Medicaid FFS is billed and what NPIs are used (including clinic and pharmacy NPIs). This decision may also affect the setup of TPA software; patient billing systems, on both the clinic and pharmacy settings; and wholesaler account setup. |  | X
CR - 6 | Register eligible sites in OPAIS | OPAIS registration is open during the first 15 days of each calendar quarter for an effective date the first day of the following quarter. Use the information gathered above on lines CR - 1 and CR - 5 to register each associated site, including appropriate NPIs (if carving in) and shipping addresses. |  | X
CR - 7 | Ensure that CE information is accurate on OPAIS | Verify the site listing, accurate representation of Medicaid carve in/out status, and updated contact information. |  |  | X
CR - 8 | Contact wholesaler to set up 340B accounts | Most wholesalers have a standard process for opening the appropriate accounts based on the CE type, but it may take up to 8 weeks to set up new accounts, so it is good to alert your wholesaler partners early. This step should be completed for any distributor or supplier from which the site purchases, not just the primary wholesaler. If you do not already have a wholesaler account, you can access the list of PVP authorized distributors (and their contacts) at the link provided. |  |  | X
CR - 9 | Identify state-specific requirements for Medicaid FFS and MCO and ensure that your systems are set up to comply | In addition to ensuring accurate information on the Medicaid Exclusion File for Medicaid FFS, sites should understand what additional elements are required by any state for which they bill Medicaid and product used was purchased at 340B. Many states have additional billing elements to identify products purchased at 340B if CE is carving in and must be incorperated into billing systems prior to going live. Sites should reach out to their state to understand specific billing requirements, but the following link may be a reference to help get you started. |  |  | X
CR - 10 | Develop regular audit plans | Ongoing program audits are critical for maintaining the integrity of the program. The PVP has developed a series of self-audit tools to help guide this process, but each site may develop its own audits and frequency based on its unique operations. Best practice sites complete self-audits at least quarterly. |  |  |  | X
CR - 11 | Prepare for HRSA audit | Develop a plan for how you will respond if HRSA were to select you for an audit. This includes knowing who to involve within your organization, understanding how to quickly pull together the the information requested by HRSA, and having a communication plan within your leadership team to provide appropriate updates in a timely manner. Keeping all of the necessary records in a single location such as a shared drive or cloud based platform can help make the process of responding to HRSA more smooth. |  |  |  |  | X
CR - 12 | Establish process for responding to noncompliance | It is important that once you do identify an issue of noncompliance, your site has a process to resolve these issues. This typically involves repayment to the manufacturer and potentially reporting to HRSA. New CEs will need to define a materiality threshold for reporting to HRSA. |  |  |  | X
CR - 13 | Understand expectations for annual recertification | HRSA expects all covered entities to recertify annually. Specific recertification window dates vary from year to year, but each year HRSA will send a notification to both the authorizing official and primary contact with details. |  |  |  |  | X
CR - 14 | Use HRSA FAQs to find guidance on many compliance elements | FAQs are written by HRSA to address a variety of common questions. These FAQs can be searched or scanned by topic. Many FAQs are available on the HRSA website, and additional FAQs are available by reaching out to Apexus Answers. | [5 empty] | X
CR - 15 | Use Apexus Answers to help with 340B or PVP questions | Apexus Answers is a free service that offers technical assistance for many 340B questions. If you can't find your answers anywhere else, reach out to Apexus Answers to see if they have additional resources to direct you to. | [5 empty] | X
Education and Training
ET - 1 | Learn the basics about the 340B Program | 340B University OnDemand is series of online educational modules that you can access at any time. Completion of OnDemand may help key members of the go-live team understand 340B Program requirements when developing the project plan. |  | X
ET - 2 | Develop training plan for staff | Developing a training plan for staff can help ensure that your team is ready to go live. You can review the list of OnDemand modules and assign some or all of these modules to staff, depending on their role. Roles to consider for education may include dispensing, puchasing, billing, auditing, operations, and leadership. Those who may be only minimally involved in the program may not want to sign up for OnDemand, so a link is provided for just the Basics module for easy access. |  |  | X
ET - 3 | Create onboarding/training plan for new staff | It is important to ensure that even after going live, all new staff who will be working with the 340B Program receive proper training. The education resources found on line ET - 1 and ET - 2 can be combined with internal references and tools to familiarize staff to their role in maintaining program integrity. |  |  |  | X
ET - 4 | Create annual staff competancy for 340B | It is a best practice to ensure that staff maintain ongoing training in the 340B Program. Many sites build their own competencies or use 340B University resources to complete annual refreshers for staff. |  |  |  |  | X
Purchasing Optimization
PO - 1 | Enroll in the PVP to access 340B Program contract savings | As the 340B Prime Vendor, Apexus negotiates sub-340B pricing and other discounts with many manufacturers. This program is available to any covered entity at no cost to the entity. However, sites must take the additional step of enrolling in the PVP to see these contracts loaded on their accounts. |  |  | X
PO - 2 | Verify with your wholesaler(s) that PVP contracts are loaded | Reach out to your wholesaler representative for a listing of all 340B accounts. Verify with the wholesaler that PVP contracts have been loaded to all accounts. The 340B PVP Catalog can be a good resource to identify contract pricing and other price types that you should expect to see on your accounts. |  |  | X
PO - 3 | Get access to the PVP participant site and delegate who will need access to the catalog | The PVP participant website has a variety of resources. Getting access for your team early can ensure that they are able to access resources mentioned in this checklist early. The catalog is the most commonly used resource on this page and is helpful for verifying pricing information. |  |  | X
PO - 4 | Update site profile on PVP website | Once you have a PVP participant site sign-on, you are able to log into 340Bpvp.com, click on your button in the upper right corner, select "my profile," and select a specific site. Here you can review your site's information in the PVP system, make changes to the primary distributor, and add/change contacts for your site. Contacts added will automatically receive Contract Updates and will receive an email asking them to create a sign-on for the PVP participant site. |  |  |  | X
PO - 5 | Sign up for regular contract announcements through Contract Updates | The PVP sends monthly Contract Updates to all participants. To sign up, send an email to Apexus Answers and include the name, title, and email address for anyone making puchasing decisions. |  |  |  | X
PO - 6 | Audit accounts to ensure contract load accuracy and pricing accuracy | The PVP site also contains a downloadable catalog that sites can use to compare product pricing to their wholesaler catalog. This can be especially important at account setup. One important thing to note is that small discrepancies may exist between the two sources of information because of factors such as wholesaler cost-minus and distribution fees. There are also price lists available for specific classes of products commonly used by grantees for quick reference. | [5 empty] | X
Note on C6: Helpful Hint: In addition to registration of sites, consider ship to addresses that may need to be added to those sites. A ship to address is typically used for any entity owned pharmacies that have their own ordering accounts or addresses. They may also be needed if product is shipped to other sites were the product still belongs to the CE, such as a repackager or a lab.
Note on C7: Helpful Hint: If your site does not have these expertise internally, evaluate the need for external resources (legal, consultants, auditors). 340B Tool: Independant Audit Request for Proposal Checklist
Note on C10: Helpful Hint: If your clinic does not bill Medicaid patients (at all), you should elect to "carve out" during the registration process.
Note on C13: Helpful Hint: This step will take 4-8 weeks depending on your wholesaler and your operations. Alerting your wholesaler of the upcoming change will allow them to work with you throughout the planning process. Your wholesaler will likely require your registration to first be approved by HRSA before they can set up accounts.
Note on C25: Helpful Hint: Annual 340B training can be tracked in 340B University OnDemand. When staff re-watch a specific module, the module completion date is updated with corresponding time stamp. An important element in creating your staff training will be incorperating your own site's operational implementation of the subjects covered in the resources provided. Many sites find it best to add an additional training element (via module development, P&P review, or other means) to incorperate expectations for staff at their site.
OnDemand Modules: 340B & Medicaid; HRSA's Medicaid Exclusion File
OPAIS Registration Guide
HRSA Audit Overview
340B Tool: Sample HRSA 340B Audit Data Request List (DRL) for Covered Entities
OPAIS Registration Guide
OnDemand Module: 340B Drug Delivery Models
340B Tool: Medicaid Exclusion File (MEF) Checklist
Validate on OPAIS
State Medicaid Profiles
340B Tool: Self-Audit: Policy and Procedure
340B Tool: Self-Audit: Contract Pharmacy
340B Tool: Sample Title X Policy and Procedure Manual
340B Tool: Establishing Material Breach Threshold
340B Tool: Self-Disclosure to HRSA and Manufacturer Template
HRSA FAQs
Apexus Answers
Apexus Answers
340B University OnDemand
Description of OnDemand Modules
Introduction to 340B Video
340B Tool: C-Suite Guide to the 340B Program
Enroll in PVP
340B PVP Catalog
Request Access
PVP Catalog
Product Information: Purchasing Decision Support
340B Tool: Medicaid Exclusion File (MEF) Checklist
PVP Authorized Distributors
340B Tool: Sample Hemophilia Treatment Center Policy and Procedure Manual
340B Tool: Sample Title X Policy and Procedure Manual
340B Tool: Sample Hemophilia Treatment Center Policy and Procedure Manual